## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | 2021 NTFB Marathon Planning Schedule
Enter Company Name in cell B2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Gantt Chart | Project Start: | 2020-08-31
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: | 1900-02-16 |  |  | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30 | [6 empty] | 2021-09-06 | [6 empty] | 2021-09-13
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-07-26 to 2021-09-19
WBS Code | TASK | ASSIGNED TO | START | END | DAYS | time axis 2021-07-26 to 2021-09-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Phase 1
1.1 | Develop a course map | Logisitics Team | 2020-08-31 | 2020-09-18 | 19
2.1.1 | Approach previous Sponsors to open discussions | Sponsor Team | 2020-09-01 | 2020-11-30 | 91
2.1.2 | Approach new sponsors, begin negotiations, and form agreements | Sponsor Team | 2020-09-01 | 2020-11-30 | 91
1.1.1 | Create a site plan | Logisitics Team | 2020-09-21 | 2020-10-02
2.2.1 | Draft Budget | Finance Team | 2020-12-01 | 2020-12-31
Phase 2
2.2.2 | Recruit additional staff for setting up race committee | Human Resources | 2021-01-01 | 2021-02-26 | 57
3.1.1 | Create and promote website | Marketing Team | 2021-01-01 | 2021-01-31 | 31
3.2.1 | Create and order print pieces | Marketing Team | 2021-01-08 | 2021-01-31
3.3.1 | Create radio and TV ads | Marketing Team | 2021-01-08 | 2021-01-31
3.4.1 | Create social media accounts | Marketing Team | 2021-02-01 | 2021-02-08
2.2.5 | Oversee registration | Registration Team | 2021-02-01 | 2021-09-03
3.3.2 | Buy airtime for advertising | Marketing Team | 2021-02-01 | 2021-09-05
3.2.2 | Distribute print pieces | Marketing Team | 2021-02-01 | 2021-03-01
3.4.2 | Create and post content on social media accounts | Marketing Team | 2021-02-01 | 2021-09-05
2.2.3 | Assign roles and responsibilities | Scheduling Team | 2021-03-01 | 2021-03-15 | 15
3.5.1 | Create and order merchandise | Marketing Team | 2021-03-01 | 2021-03-31
1.2.1 | Acquire all necessary insurance documents | Logisitics Team | 2021-03-15 | 2021-03-29 | 15
2.2.4 | Create tasks and timelines | Scheduling Team | 2021-03-15 | 2021-04-07 | 24
Phase 3
3.5.2 | Mail race packages to runners | Marketing Team | 2021-04-01 | 2021-04-30
2.3.1 | Make arrangements for conducting Expo | Event Organizers | 2021-04-01 | 2021-05-31 | 61
2.3.2 | Shortlist vendors | Vendor Selection Committee | 2021-05-01 | 2021-05-17
1.2.2 | Acquire necessary licenses and permits | Logisitics Team | 2021-05-24 | 2021-06-14
2.3.3 | Create vendor agreements and contracts | Event Administrators | 2021-06-01 | 2021-06-15
4.2.3 | Organize volunteers for spectator activities | Management Staff | 2021-06-01 | 2021-06-15
4.3.1 | Plan award ceremony and other award materials | Management Staff | 2021-06-01 | 2021-09-01
2.4.1 | Collaborate and coordinate with third party labor workers | Event Assistants | 2021-07-01 | 2021-07-15
4.3.2 | Organize volunteers to obtain trophies and other award materials | Activity Planning Team | 2021-07-01 | 2021-09-05
5.1.2 | Assign medical team to follow runners to handle medical emergencies and set up mobile hospitals at appropriate intervals. | Medical (Safety)Team | 2021-07-05 | 2021-09-05
5.1.3 | Contract Event Paramedic Services | Medical (Safety)Team | 2021-07-05 | 2021-09-05
5.3.2 | Employ Event Security Services | Security Department | 2021-07-05 | 2021-09-05
1.1.4 | Do a test run | Logisitics Team | 2021-07-05 | 2021-07-19 | 15
1.2.3 | Submit Outdoor Events Application | Logisitics Team | 2021-07-05 | 2021-07-12 | 8
2.4.2 | Plan after marathon schedule | Event Assistants | 2021-07-15 | 2021-07-30 | 16
1.1.3 | Schedule road closures and secure signage | Logisitics Team | 2021-07-23 | 2021-08-05 | 14
Phase 4
1.3.1 | Rent generators | Logisitics Team | 2021-08-02 | 2021-08-16
1.4.1 | Rent essentials for site | Logisitics Team | 2021-08-02 | 2021-08-16
4.2.2 | Prepare Marathon Trivia | Activity Planning Team | 2021-08-02 | 2021-09-05
4.3.3 | Designate of find one or two hosts for award ceremony | Activity Planning Team | 2021-08-02 | 2021-09-05
2.4.3 | Contact and contract videography/photograpy | Technical Support Team | 2021-08-05 | 2021-09-03
5.3.4 | Organize installation and drone rentals and CC TV system | Security Department | 2021-08-05 | 2021-09-05
5.2.0 | Create Emergency Information Maps | Risk Management Team | 2021-08-05 | 2021-09-05
4.1.1 | Find a DJ | Activity Planning Team | 2021-08-06 | 2021-09-05
1.2.4 | Make information packets | Logisitics Team | 2021-08-16 | 2021-08-30
4.2.1 | Set up Spectator activity booth | Activity Planning Team | 2021-08-23 | 2021-09-05
1.1.2 | Create a traffic control plan | Logisitics Team | 2021-08-23 | 2021-09-03
1.1.5 | Mark booth locations, stations, and cheer spots; hang banners and put up mile markers | Logisitics Team | 2021-08-30 | 2021-08-31
1.5.1 | Set up stage and lights | Sound Team | 2021-09-01 | 2021-09-02
1.1.6 | Coordinate installation of temporary accessibility ramps | Logisitics Team | 2021-09-02 | 2021-09-03 | 2
1.3.2 | Inspect electrical system and stage | Logisitics Team | 2021-09-03 | 2021-09-03 | 1
1.4.2 | Set up equipment rentals | Logisitics Team | 2021-09-03 | 2021-09-04 | 2
1.5.2 | Set up PA system | Sound Team | 2021-09-04 | 2021-09-04 | 1
1.5.3 | Check PA system | Sound Team | 2021-09-05 | 2021-09-05 | 1
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.