## Sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
1.1.1 Create WBS
1.2.1 Create Gantt Chart
1.2.1 Agree on tasks per group member
1.3.1 Meet weekly
1.3.2 Email via Canvas
1.4.1 Review and revise plan as necessary
2.1.1 Define organization
2.1.2 Identify stakeholders
2.2.1 Analyze content
2.2.2 Evaluate competitors (benchmarking)
2.2.3 Review existing metadata
2.3.1 Interview users
3.1.1 Analyze results from user interviews
3.1.2 Develop personas
3.2.1 Agree on new labels
3.2.2 Carry out card sort survey
3.2.3 Analyze results from card sort survey
4.1.1 Build blueprint of suggested navigation and labeling
4.1.2 Create wireframes of suggested page layouts
4.2.1 Take inventory of content on website
4.2.2 Determine what content goes where in new design
4.3.1 Create controlled vocabulary for website
5.1.1 Create architecture of site in Drupal
5.1.2 Copy content onto pages from existing site.
5.1.3 Replicate page layouts from wireframes.
6.1.1 Write report and compile all graphics to convey suggested changes to site
6.1.2 Review report for coherence and errors, including spelling and grammar
| 1. Plan | 2. Research | 3. Strategy | 4. Design | 5. Implement | 6. Report